## Sheet1
Number | Planned start date | Planned end date | Planned Outage Start | Planned Outage End | Short description | Change Request CI Rollup | Disruptive | State | Requested by | Category | Reason | Assigned to | Coverage | Off Shore L1 | L1 | L2 | L2 Team App POCs | Pipeline Yes/No | Milestone Issues Y/N | Process Improvements Recommendations | Did L1 implemented? Y/N | If L1 did not implement? Why not? | Follow-ups
CHG000253255 | 2019-11-05 06:19 | 2019-11-05 10:00 |  |  | Release 2019_11_05 | REBV - Prime Biller |  | Closed | Nuthoo, Naz | Application Software | Enhancement |  | In Scope |  | N/A | N/A | Michele Janders Michelle Rubio | No | N |  |  |  | Not preformed by our group
CHG000252045 | 2019-11-05 18:00 | 2019-11-05 19:00 |  |  | Deployment for Resporg Prod Issues | SW5V - Toll Free Order Management | No | Closed | Indukuri, Venkatapathi Raju | Application Software | Fix | Sanders, Chester L | In Scope |  | Venkat Gollapudi |  | Gilbert Perez Chet Sanders Raju Indukuri Venkatapathi Poojitha Ponnam
CHG000252818 | 2019-11-05 19:00 | 2019-11-06 23:00 |  |  | TFNM Legacy Deployment -EVS Code change | TFNV - Toll Free Network Manager | No | Closed | Vaghasia, Aditi | Application Software | Enhancement |  | In Scope | N/A | Venkat Gollapudi | Surendra Perugupalli | Ricky Bond Surendra Perugupalli | No
CHG000250565 | 2019-11-05 23:00 | 2019-11-06 06:00 |  |  | Update wsvp SSI - LSIPRD OCI DB link - NOV 05 2019- Screener/VAD | ETQV - Enterprise Screener - Vz Business | No | Closed | Janders, Michele J | Application Software | Maintenance |  | In Scope | N/A | Venkat Gollapudi | Michele Janders | Michele Janders | No | N | Need pipeline |  |  | being performed by VDSI - Ashok Billakanti
CHG000252319 | 2019-11-06 20:30 | 2019-11-07 06:00 |  |  | IPTS S2 - Real Time Monitoring status for DE,Conf,Conf_VRD and GPS | FHOV - Internet Protocol Traffic System Strategic Services | No | Closed | Rani, Undavalli | Application Software | Maintenance | Rani, Undavalli | In Scope |  | Venkat Gollapudi |  | Jae Cho Steven Copley
CHG000219377 | 2019-11-07 05:30 | 2019-11-07 07:30 | 2019-11-07 05:30 | 2019-11-07 07:30 | Apply Quarterly Security Patch to Oracle Binaries | ISZV - International Statistical Tracing and Reporting System | Yes | Closed | Hall, William | Database | Maintenance | Hall, William | In Scope |  | N/A |  | ?
CHG000223598 | 2019-11-07 05:49 | 2019-11-07 07:20 |  |  | INMP change 2019.11.1 | NMIV - International Network Mediation Processor | No | Implement | Basu, Rozaliva | Application Software | Maintenance | Basu, Rozaliva | In Scope |  | N/A |  | ?
CHG000250047 | 2019-11-07 08:00 | 2019-11-08 |  |  | BODS Release I - Nov 2019 | FTKV - Billing Operational Data Store | No | Implement | Vasudevan, Sasithar X | Application Software | Enhancement | Maddi, Mithun | In Scope | N/A | N/A | N/A | Denise Dege Ken Lingold | N/A | N/A | N/A | N | not involved with BODS releases
CHG000250063 | 2019-11-07 08:00 | 2019-11-08 |  |  | Production Support Enhancements I - Nov 2019 | FTKV - Billing Operational Data Store | No | Implement | Vasudevan, Sasithar X | Application Software | Maintenance | Maddi, Mithun | In Scope | N/A | N/A | N/A | Denise Dege Ken Lingold | N/A | N/A | N/A | N | not involved with BODS releases
CHG000253831 | 2019-11-07 09:00 | 2019-11-07 10:00 |  |  | PB CLIDS scripts have been failing due to SV10 perl upgrade | REBV - Prime Biller | No | Implement | Nuthoo, Naz | Application Software | Fix | Nuthoo, Naz | In Scope |  | N/A |  | Michele Janders Michelle Rubio | No
CHG000251739 | 2019-11-07 10:00 | 2019-11-07 16:00 |  |  | Perform Migration in RYE Mainframe | GVBV - Global Communication Services Billing System | No | Assess | Nolan, Lawrence J | Batch Job | Maintenance | Dege, Denise M | In Scope | N/A | N/A | Denise Dege | Denise Dege | N/A | Y | None | N | no L1 needed for this task | Approvers didn't approve in time, so I didn't do the migration. Developer will have to find a new time and try again.
CHG000253642 | 2019-11-07 10:04 | 2019-11-07 11:04 |  |  | Add Supplemental Logging on tables | REBV - Prime Biller | No | Authorize | Williams, Julius | Database | Enhancement | Williams, Julius | In Scope |  | N/A |  | Michele Janders Michelle Rubio | No
CHG000244892 | 2019-11-07 12:00 | 2019-11-07 13:30 | 2019-11-07 12:00 | 2019-11-07 13:30 | Apply Quarterly Security Patch to Oracle Binaries | IMMV - International Message Analysis andPresentation System | Yes | Scheduled | Hall, William | Database | Maintenance | Hall, William | In Scope |  | N/A |  | ?
CHG000251982 | 2019-11-07 16:00 | 2019-11-07 17:00 |  |  | Billing Gateway November charge code 2019 release implementation | BGAV - Billing Gateway | No | Scheduled | Dutta, Suparna | Application Software | Enhancement | Dutta, Suparna | In Scope | N/A | N/A | Denise Dege | Denise Dege Ken Lingold | N/A | N | None | N | no L1 needed for this task
CHG000251920 | 2019-11-07 19:00 | 2019-11-08 06:00 |  |  | Iorder 2.0Weekly release | IO1V - iOrder V19G - Verizon Enterprise Center V20G - Verizon Business Center | No | Scheduled | Ranjan, Anish X | Application Software | Maintenance |  | In Scope | N/A | N/A |  | ?
CHG000253779 | 2019-11-07 21:00 | 2019-11-08 04:00 |  |  | F50V - Point Release 11/7/2019 21:00 EST | F50V - vPrice | Yes | New | Copley, Steven J | Application Software | Enhancement | Copley, Steven J | In Scope | N/A | Venkat Gollapudi |  | Venkat Gollapudi Qamar Khan Jae Cho Steven Copley | No
CHG000251916 | 2019-11-07 22:00 | 2019-11-08 06:00 |  |  | VEC 1.0 application patch | TFNV - Toll Free Network Manager V19G - Verizon Enterprise Center V20G - Verizon Business Center | No | Scheduled | Ranjan, Anish X | Application Software | Maintenance | Ranjan, Anish X | In Scope | N/A | Venkat Gollapudi |  | Ricky Bond Surendra Perugupalli | No |  |  |  |  | VES_V19G_VEC_SUPPORT is implementing this change
CHG000252727 | 2019-11-07 23:00 | 2019-11-08 04:00 |  |  | Applying SSO fields to header for MDM and app verification once complete applying SSO implment PF637082050900499 | BOYV - Master Data Management Portal | No | Scheduled | Elzamzami, Elzamzami M | Application Software | Enhancement | Akins, Stephen J | In Scope | N/A | Venkat Gollapudi | Jeff Akins | Sowmya Reddy Jae Cho Jeff Akins | No
CHG000252317 | 2019-11-08 05:00 | 2019-11-08 06:00 |  |  | MW updates on eusodb-control1.ams.ops.eu.uu.net | B1RV - EPS Database Monitoring |  | Scheduled | Perka, Kamil | Hosting Services | Maintenance | Kalab, Petr | In Scope | N/A | N/A |  | Ab's Team
CHG000253757 | 2019-11-08 05:45 | 2019-11-08 10:45 | 2019-11-08 05:45 | 2019-11-08 10:45 | ITRSchanges | ITJV - International Traffic Reporting System | Yes | Assess | Basu, Rozaliva | Application Software | Maintenance | Basu, Rozaliva | In Scope |  | N/A |  | ?
CHG000250380 | 2019-11-08 22:00 | 2019-11-09 01:00 |  |  | RULE NUMBER : 190953, 190955,190956- Casino Changes for onmv2.verizon.com,nmv2.verizon.com and nmlitev2.verizon.com inLB SAC/TPA | TFNV - Toll Free Network Manager | No | Authorize | Bhaniramka, Akhilesh | Network Services | Enhancement |  | In Scope |  | Tanmay Mahesh Kumar |  | Ricky Bond Surendra Perugupalli | No
CHG000238335 | 2019-11-09 21:00 | 2019-11-10 04:00 |  |  | BAU - DASD REORG, Backups, and IPL for IXplus systems.IXPRODA, IXPRODB, IXPRODC, IXPRODE, IXPRODK, IXPRODS | IXPV - IXPlus |  | New | Curtis, Greg E | Storage and Back-Up Services | Maintenance | Gandy, Vincent | In Scope | N/A | N/A | Lim Davis | Lim Davis |  |  |  | Y |  | BAU job for backups. No follow up needed.
CHG000252699 | 2019-11-01 18:00 | 2019-11-01 21:00 |  |  | DB Changes in GCH Production 2.0 | GCHV - Global Customer Hierarchy | No | New | Bandi, Srivarsha | Application Software | Enhancement |  | Impact Only | N/A | N/A | N/A | N/A
CHG000252412 | 2019-11-01 21:00 | 2019-11-02 06:00 |  |  | Reschedule OS patching forVEC prod FRDserver vpbfdpd09-12old change was CHG000243875 | V19G - Verizon Enterprise Center | No | New | Xie, Zhenwei | Database | Maintenance | Xie, Zhenwei | Impact Only | N/A | N/A | N/A | N/A
CHG000253265 | 2019-11-05 07:27 | 2019-11-05 07:37 |  |  | Production change - VERT-3967 | V19G - Verizon Enterprise Center |  | Closed | Sakhamudi, SrinivasaRao X | Database | Maintenance |  | Impact Only | N/A | N/A | N/A | N/A
CHG000253151 | 2019-11-05 09:00 | 2019-11-05 15:00 |  |  | BLM - Prework needed for future migration | A5SV - Managed Services Platform – Fault Management | No | Closed | Rodriguez, Marco A | Application Software | Enhancement | Rodriguez, Marco A | Impact Only | N/A | N/A | N/A | N/A
CHG000253363 | 2019-11-05 11:40 | 2019-11-06 11:40 |  |  | Resize OCI VM | FETV - Verizon Application Performance - Early Warning System | No | Closed | Chikode, Neil A | OCI Infrastructure | Enhancement | Mirza, Asif J | Impact Only | N/A | N/A | N/A | N/A
CHG000253360 | 2019-11-05 14:00 | 2019-11-05 23:00 |  |  | Movenew proxy toAWS APIGEE prod TO AMEX BRIDGESTONE | VBEV - Verizon Business Ebonding Solutions | No | Implement | Medasani, Sitaram Prasad | Application Software | Maintenance | Medasani, Sitaram Prasad | Impact Only | N/A | N/A | N/A | N/A
CHG000253401 | 2019-11-05 16:01 | 2019-11-05 18:01 |  |  | Normalize ETMS in FRD on October 2019.3 Release | TMMV - Enterprise Trouble Management System | No | Closed | Hewitt, David A | Application Software | Maintenance | Hewitt, David A | Impact Only | N/A | N/A | N/A | N/A
CHG000252425 | 2019-11-05 19:00 | 2019-11-06 04:01 |  |  | LB certs renewal for VEC 2.0 | WF1V - Verizon Enterprise Solutions - Workflow Management | No | Implement | Konepalli, Puja | Application Software | Maintenance | Inumula, Abhiram | Impact Only | N/A | N/A | N/A | N/A
CHG000249652 | 2019-11-05 21:00 | 2019-11-06 01:00 |  |  | GSLB changes on proquest.verizon.com LB to add OCI VIP's LB Request 191210 | EKYV - ProQuest | No | Closed | Kotapati, Vamsi | Network Services | Enhancement | Cazzola, Daniel B (DANNY) | Impact Only | N/A | N/A | N/A | N/A
CHG000250473 | 2019-11-05 22:00 | 2019-11-06 05:00 |  |  | PQ need to Bypass SSO for ProQuest Archive Keepalive- PF637075964495102 | EKYV - ProQuest | No | Implement | Kotapati, Vamsi | Application Software | Maintenance | Cooper, Ryan B | Impact Only | N/A | N/A | N/A | N/A
CHG000253577 | 2019-11-06 02:50 | 2019-11-06 03:20 |  |  | Production change - VERT-3969 | V19G - Verizon Enterprise Center |  | Closed | Sakhamudi, SrinivasaRao X | Database | Maintenance |  | Impact Only | N/A | N/A | N/A | N/A
CHG000253609 | 2019-11-06 08:06 | 2019-11-06 08:36 |  |  | V19G Database deployment | V19G - Verizon Enterprise Center |  | Closed | Sakhamudi, SrinivasaRao X | Database | Maintenance |  | Impact Only | N/A | N/A | N/A | N/A
CHG000253096 | 2019-11-06 09:00 | 2019-11-06 11:23 |  |  | Maintenance CA – IntradaPro 20191106 | IROV - IntradaPro | No | Implement | Tadikonda, Uma | Application Software | Enhancement | Kothapally, Chandra Prakash | Impact Only | N/A | N/A | N/A | N/A
CHG000253630 | 2019-11-06 09:25 | 2019-11-06 09:55 |  |  | Production change - VERT-3971 | V19G - Verizon Enterprise Center |  | Closed | Sakhamudi, SrinivasaRao X | Database | Maintenance |  | Impact Only | N/A | N/A | N/A | N/A
CHG000253486 | 2019-11-06 10:00 | 2019-11-06 17:00 |  |  | SMARTS - D113 updates - svc account - part3 | A5SV - Managed Services Platform – Fault Management | No | Closed | Rodriguez, Marco A | Application Software | Enhancement | Rodriguez, Marco A | Impact Only | N/A | N/A | N/A | N/A
CHG000253035 | 2019-11-06 10:00 | 2019-11-06 18:00 |  |  | Rebuild OCI Non Prod Servers. | EG1V - Advanced Message Queuing Platform | No | Implement | Mohammed, Sohail Sadasivpet | Storage Services | Maintenance | Mohammed, Sohail Sadasivpet | Impact Only | N/A | N/A | N/A | N/A
CHG000252083 | 2019-11-06 10:00 | 2019-11-06 19:00 |  |  | IPTS VOIP OCI Prod Application installation Part 2 - Rpt & BS server | IPIV - Internet Protocol Traffic System | No | Closed | Subramaniyan, Venkatesan X | Application Software | Maintenance | Subramaniyan, Venkatesan X | Impact Only | N/A | N/A | N/A | N/A
CHG000249359 | 2019-11-06 17:00 | 2019-11-07 06:00 |  |  | PQ Catalog load | EKYV - ProQuest |  | Implement | Kotapati, Vamsi | Application Software | Enhancement |  | Impact Only | N/A | N/A | N/A | N/A
CHG000252696 | 2019-11-06 18:00 | 2019-11-06 21:00 |  |  | USP(CMDB 2.0)FIX | DT2V - Configuration Management Data Base | No | Implement | Chinnam, Avinash | Application Software | Maintenance | Chinnam, Avinash | Impact Only | N/A | N/A | N/A | N/A
CHG000253069 | 2019-11-06 20:00 | 2019-11-06 22:00 |  |  | BAU - SSL Cert update | TLDV - Traffic Reporting System | No | Closed | Oduri, Sailesh | Security Services | Maintenance | Gorantla, Prasanth | Impact Only | N/A | N/A | N/A | N/A
CHG000250193 | 2019-11-06 21:00 | 2019-11-07 07:00 |  |  | This Change is used forupdating the Heap Memory for bmx managed servers for orderpro | OPEV - OrderPro | No | Implement | Moparthi, Sudheer Kumar | Application Software | Enhancement | Moparthi, Sudheer Kumar | Impact Only | N/A | N/A | N/A | N/A
CHG000253112 | 2019-11-06 22:00 | 2019-11-07 03:00 |  |  | CMDBWeekly deployment | DT2V - Configuration Management Data Base SPXV - Service Profile Inventory Manager | No | Implement | Chinnam, Avinash | Application Software | Enhancement |  | Impact Only | N/A | N/A | N/A | N/A
CHG000252593 | 2019-11-06 22:00 | 2019-11-07 08:00 |  |  | NPANXX Datasource migration | IRJV - International Rates Management | No | New | Cherukumalli, Srinivasa R | Middleware | Enhancement | Cherukumalli, Srinivasa R | Impact Only | N/A | N/A | N/A | N/A
CHG000253640 | 2019-11-06 22:30 | 2019-11-07 05:00 |  |  | Cloud VISE Oct'19 hotfix deployment | EKYV - ProQuest |  | Implement | Chilupuri, AshokKumar X | Application Software | Enhancement |  | Impact Only | N/A | N/A | N/A | N/A
CHG000253840 | 2019-11-06 23:00 | 2019-11-07 04:00 |  |  | EKYV: K8s: Prod Deployment | EKYV - ProQuest |  | Implement | Krishnan, Raghuram X (Ram Krish) | Application Software | Enhancement |  | Impact Only | N/A | N/A | N/A | N/A
CHG000253854 | 2019-11-07 02:13 | 2019-11-07 02:23 |  |  | Production change - VERT-3963 | V19G - Verizon Enterprise Center |  | Closed | Sakhamudi, SrinivasaRao X | Database | Maintenance |  | Impact Only | N/A | N/A | N/A | N/A
CHG000251385 | 2019-11-07 05:00 | 2019-11-07 07:00 |  |  | Unsupported Java version needs to be removed from the Linux DB servers | UIIV - Utility Information Services | No | Authorize | Faure, Sonia S | Unix Services | Maintenance | Faure, Sonia S | Impact Only | N/A | N/A | N/A | N/A
CHG000253617 | 2019-11-07 06:00 | 2020-01-06 06:00 |  |  | PremiSys OCI Non-Prod Host Decom - 63-21-75-143 | B4EV - PremiSys | No | Canceled | Mekala, Kulasekhar | Configuration Items | Decommission | Mekala, Kulasekhar | Impact Only | N/A | N/A | N/A | N/A
CHG000253890 | 2019-11-07 07:30 | 2019-11-07 08:00 |  |  | V19G Database deployment | V19G - Verizon Enterprise Center |  | Closed | Sakhamudi, SrinivasaRao X | Database | Maintenance |  | Impact Only | N/A | N/A | N/A | N/A
CHG000252422 | 2019-11-07 08:00 | 2019-11-07 23:59 |  |  | Nov 7th 2019 - Offcycle release for OBUS - Batch Job | OBUV - Online Customer Information System (OCIS) for Business | No | Implement | Ramesh, Chatari S | Batch Job | Enhancement | Vbangole, Arvindkumar | Impact Only | N/A | N/A | Denise Dege | N/A
CHG000252427 | 2019-11-07 08:00 | 2019-11-07 23:59 |  |  | COMS Nov 7th 2019 Offfcycle release at NOR2 LPAR Mainframe | COZV - Circuit Order Management System | No | Implement | Ramesh, Chatari S | Application Software | Enhancement | Ramesh, Chatari S | Impact Only | N/A | N/A | Denise Dege | N/A
CHG000250627 | 2019-11-07 08:00 | 2019-11-08 |  |  | VESDW Release I - Nov 2019 | ZDWV - VES Data Warehouse | No | Implement | Vasudevan, Sasithar X | Application Software | Enhancement | Maddi, Mithun | Impact Only | N/A | N/A | N/A | N/A
CHG000251774 | 2019-11-07 08:00 | 2019-11-11 23:00 |  |  | VBIS/CC -Nov 2019 Offcycle Release (11/8/19) | BKZV - Verizon Business Incentive System | No | Assess | Galasso, Andrew | Application Software | Fix | Galasso, Andrew | Impact Only | N/A | N/A | N/A | N/A
CHG000251778 | 2019-11-07 08:00 | 2019-11-11 23:00 |  |  | SPA -Nov 2019 Offcycle Release (11/8/19) | SP3V - Sales Planning and Analysis Reporting | No | Assess | Galasso, Andrew | Application Software | Enhancement | Galasso, Andrew | Impact Only | N/A | N/A | N/A | N/A
CHG000251780 | 2019-11-07 08:00 | 2019-11-11 23:00 |  |  | STM -Nov 2019 Offcycle Release (11/8/19) | SH2V - Sales Team Manager | No | Assess | Galasso, Andrew | Application Software | Enhancement | Galasso, Andrew | Impact Only | N/A | N/A | N/A | N/A
CHG000253914 | 2019-11-07 08:15 | 2019-11-07 08:45 |  |  | Production change - VERT-3976 |  |  | Closed | Sakhamudi, SrinivasaRao X | Database | Maintenance |  | Impact Only | N/A | N/A | N/A | N/A
CHG000250155 | 2019-11-07 09:00 | 2019-11-07 14:00 |  |  | OS Upgrade of the productive iLTC servers | BBYV - iServe - Lead Time Calculator | Yes | Implement | Buckner, Ralf | Hosting Services | Maintenance | Buckner, Ralf | Impact Only | N/A | N/A | N/A | N/A
CHG000252197 | 2019-11-07 13:00 | 2019-11-07 18:00 |  |  | RACE November 2019 Release;PR00022949-CFO - Revenue & Leasing Systems | RCLV - Revenue Accounting Close Engine | No | Scheduled | Schepers, Michael J | Application Software | Enhancement | Schepers, Michael J | Impact Only | N/A | N/A | N/A | N/A
CHG000253473 | 2019-11-07 18:00 | 2019-11-07 23:59 |  |  | SMARTS Weekly Release 11/07 | A5SV - Managed Services Platform – Fault Management | No | Scheduled | Rodriguez, Marco A | Application Software | Enhancement | Rodriguez, Marco A | Impact Only | N/A | N/A | N/A | N/A
CHG000251918 | 2019-11-07 19:00 | 2019-11-08 06:00 |  |  | SMD-GCM 2.0 weekly maintenance release | G1FV - Global Change Management F7GV - Service Management Dashboard V19G - Verizon Enterprise Center | No | Scheduled | Ranjan, Anish X | Application Software | Maintenance |  | Impact Only | N/A | N/A | N/A | N/A
CHG000251919 | 2019-11-07 19:00 | 2019-11-08 06:00 |  |  | VECRM 2.0 weekly maintenance release | V19G - Verizon Enterprise Center G32V - Verizon Enterprise Customer Relationship Management | No | Scheduled | Ranjan, Anish X | Application Software | Maintenance |  | Impact Only | N/A | N/A | N/A | N/A
CHG000251921 | 2019-11-07 19:00 | 2019-11-08 06:00 |  |  | VEC 2.0 Suite of Application Release (Toggle Blue -Green ) | V19G - Verizon Enterprise Center V20G - Verizon Business Center |  | Scheduled | Ranjan, Anish X | Application Software | Maintenance |  | Impact Only | N/A | N/A | N/A | N/A
CHG000252361 | 2019-11-07 21:00 | 2019-11-08 02:00 | 2019-11-07 21:00 | 2019-11-08 02:00 | Update iPlanet packages VZswscdoa.ds_1.3-DOAT-SU1.Z and VZswscwes.ds_1.3-SPH1WEBSVC-SU1.Zfor vulnerability fix | A1UV - Audit Engine | Yes | Scheduled | Rizvi, Joher | Middleware | New or remove CI | Mohammed, Imran | Impact Only | N/A | N/A | N/A | N/A
CHG000251368 | 2019-11-07 21:00 | 2019-11-08 07:00 |  |  | Enable theOTS/BUCS feed in BMX. | OPEV - OrderPro | No | Scheduled | Kishore, Shivesh | Application Software | Enhancement | Kishore, Shivesh | Impact Only | N/A | N/A | N/A | N/A
CHG000246388 | 2019-11-07 21:01 | 2019-11-08 05:01 |  |  | PHX LB Rule Implementation #191039 &191037 | TMMV - Enterprise Trouble Management System | No | Authorize | Hewitt, David A | Network Services | Fix | Ojeda, Eric | Impact Only | N/A | N/A | N/A | N/A
CHG000246381 | 2019-11-07 21:01 | 2019-11-08 05:01 |  |  | Ashburn LB Rule Implementation #191038 & 191036 | TMMV - Enterprise Trouble Management System | No | Authorize | Hewitt, David A | Network Services | Fix | Ojeda, Eric | Impact Only | N/A | N/A | N/A | N/A
CHG000253032 | 2019-11-07 22:08 | 2019-11-07 23:59 |  |  | OCI - Application Server Go-Live - Net Status - Front End Web Portal (WRPV) | WRPV - Net Status - Front End Web Portal | No | Authorize | Williams, Weldon C | OCI Go Live | Enhancement | Williams, Weldon C | Impact Only | N/A | N/A | N/A | N/A
CHG000253859 | 2019-11-08 04:00 | 2019-11-08 08:00 |  |  | VTAG lodbalance Cert renewal | VTGV - Verizon Trouble Administration Gateway | No | Authorize | Subramaniyan, Venkatesan X | Application Software | Maintenance | Jagannathan, Vasudevan X | Impact Only | N/A | N/A | N/A | N/A
CHG000253250 | 2019-11-08 07:00 | 2019-11-08 20:00 |  |  | IPTS VOIP OCI Prod Application installation Part 2 - Rpt & BS server | IPIV - Internet Protocol Traffic System | No | Scheduled | Subramaniyan, Venkatesan X | Application Software | Enhancement | Subramaniyan, Venkatesan X | Impact Only | N/A | N/A | N/A | N/A
CHG000253462 | 2019-11-08 07:00 | 2019-11-08 21:01 |  |  | This change is to move the Apigee proxy c8dv-vticket-cx-proxy to production using Jenkins. | C8DV - VPS Regulatory and Business Reporting System - DSS | No | Scheduled | Williams, Weldon C | Application Software | Maintenance | Williams, Weldon C | Impact Only | N/A | N/A | N/A | N/A
CHG000253085 | 2019-11-08 12:04 | 2020-01-08 12:04 |  |  | Decommissioning old Windows servers under PMO application which are not in use anymore - OMZWDAXHVA002 | AXHV - PMO Team WorkPlace |  | New | Karri, Bhavana | Configuration Items | Decommission |  | Impact Only | N/A | N/A | N/A | N/A
CHG000253087 | 2019-11-08 12:13 | 2020-01-08 12:13 |  |  | Decommissioning PMO Window Servers 2012 R2to request new Windows 2016 servers | AXHV - PMO Team WorkPlace | No | New | Karri, Bhavana | Configuration Items | Decommission |  | Impact Only | N/A | N/A | N/A | N/A
CHG000240272 | 2019-11-08 12:38 | 2019-11-09 |  |  | MF WLN - CABS2 - BAU WEEKLY PROD CODE MIGRATION; ITMS, SPUFI | XRUB - Carrier Access Billing System | No | New | Echavez, Mark E (Mark Echavez) | Application Software | Enhancement | Echavez, Mark E (Mark Echavez) | Impact Only | N/A | N/A | N/A | N/A
CHG000251063 | 2019-11-08 18:00 | 2019-11-08 19:00 |  |  | Blockchain Process - Segregate Feeds between CTL and AT&T | ETHV - Enterprise Taxation Services System | No | Scheduled | Vera, Peter F | Application Software | Enhancement | Vera, Peter F | Impact Only | N/A | N/A | N/A | N/A
CHG000250961 | 2019-11-08 20:01 | 2019-11-09 06:00 |  |  | Migrate Netstatus database from On-Prem to OCI servers. | WRPV - Net Status - Front End Web Portal | No | Assess | Williams, Weldon C | Database | Enhancement | Williams, Weldon C | Impact Only | N/A | N/A | N/A | N/A
CHG000250887 | 2019-11-08 21:00 | 2019-11-08 22:00 |  |  | Deploy Dast fixes and decommision files | WWSV - Wholesale Web Server for Customer Support | No | Scheduled | Sundararajan, Maya | Application Software | Maintenance | Sundararajan, Maya | Impact Only | N/A | N/A | N/A | N/A
CHG000252486 | 2019-11-08 21:00 | 2019-11-09 02:00 | 2019-11-08 21:00 | 2019-11-09 02:00 | Update iPlanet packages to VZswscrsa.ds_1.3-SPH1CRSAE-SU1.Z for vulnerability fix on CRS/AE prod server (a1ufrdgpw01) | A1UV - Audit Engine | Yes | Scheduled | Mohammed, Imran | Middleware | New or remove CI | Mohammed, Imran | Impact Only | N/A | N/A | N/A | N/A
CHG000246897 | 2019-11-08 21:00 | 2019-11-09 21:00 | 2019-11-08 21:00 | 2019-11-08 21:00 | ECS OCI migration | B4UV - Export Compliance System II | Yes | Scheduled | Jadhav, Sandesh Baliram | Application Software | Enhancement | Venkatesan, Karthikayan X (Karthik) | Impact Only | N/A | N/A | N/A | N/A
CHG000251900 | 2019-11-08 21:00 | 2019-11-11 05:00 |  |  | SevOne - NDC Pod 1 Cluster 1c – Post Expansion configuration | MPMV - Managed Services Platform - Performance Management | No | Scheduled | Rodriguez, Marco A | Application Software | Enhancement | Rodriguez, Marco A | Impact Only | N/A | N/A | N/A | N/A
CHG000253358 | 2019-11-08 23:00 | 2019-11-09 06:00 |  |  | F&E BAU Monthly database maintenance November 2019 | FEBV - F&E Billing FOEV - Facilities and Engineering - Order Entry | Yes | Scheduled | Ravi, Shankaranarayanan (Ravi) | Database | Maintenance | Ravi, Shankaranarayanan (Ravi) | Impact Only | N/A | N/A | N/A | N/A
CHG000240273 | 2019-11-08 23:30 | 2019-11-09 |  |  | MF WLN- VADI - BAU WEEKLY PROD CODE MIGRATION; ITMS, SPUFI | BDIB - Verizon Advanced Data | No | New | Echavez, Mark E (Mark Echavez) | Application Software | Enhancement | Echavez, Mark E (Mark Echavez) | Impact Only | N/A | N/A | N/A | N/A
CHG000240275 | 2019-11-08 23:30 | 2019-11-09 |  |  | (BAU)-CABS2 Weekly Code Migration into Training - SOPS | XRUB - Carrier Access Billing System | No | New | Echavez, Mark E (Mark Echavez) | Application Software | Maintenance | Echavez, Mark E (Mark Echavez) | Impact Only | N/A | N/A | N/A | N/A
CHG000253440 | 2019-11-08 23:50 | 2020-01-08 23:50 |  |  | Decommission Servers - date set for 11/08/2019. | FETV - Verizon Application Performance - Early Warning System | No | Scheduled | Bhuiyan, Md R | Configuration Items | Decommission | Thiruvenkatam, Satish K | Impact Only | N/A | N/A | N/A | N/A
CHG000238331 | 2019-11-09 20:00 | 2019-11-10 04:00 |  |  | BAU-IXplus backups for IRA system | DR4V - Instruction Record Application |  | New | Curtis, Greg E | Storage and Back-Up Services | Maintenance | Gandy, Vincent | Impact Only | N/A | N/A | N/A | N/A
CHG000252485 | 2019-11-10 09:00 | 2019-11-10 12:00 | 2019-11-10 09:00 | 2019-11-10 12:00 | Apply Weblogic Patch 27919965 to FRR Analytics Production Servers | B4FV - Financial Reports Repository | Yes | Scheduled | Parkinson, Marc G | Application Software | Enhancement | Parkinson, Marc G | Impact Only | N/A | N/A | N/A | N/A
CHG000250365 | 2019-11-11 08:00 | 2019-11-11 20:00 |  |  | IPTS VOIP OCI Prod Application installation Part 3 | IPIV - Internet Protocol Traffic System | No | Assess | Subramaniyan, Venkatesan X | Application Software | Maintenance | Subramaniyan, Venkatesan X | Impact Only | N/A | N/A | N/A | N/A
CHG000251894 | 2019-11-11 09:00 | 2019-11-11 18:00 |  |  | SevOne - Upgrade Healthcluster from 5.7.2.6 to 5.7.2.11 | MPMV - Managed Services Platform - Performance Management | No | Scheduled | Rodriguez, Marco A | Application Software | Enhancement | Rodriguez, Marco A | Impact Only | N/A | N/A | N/A | N/A
CHG000253598 | 2019-11-11 22:00 | 2019-11-12 06:00 |  |  | VEC 1.0- App Servers reboot -Phase 1 | V19G - Verizon Enterprise Center V20G - Verizon Business Center | No | Assess | Ramalingam, Selvaraj X | Application Software | Maintenance |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A
| #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  |  |  |  | Impact Only | N/A | N/A | N/A | N/A